## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Setting up jira/confluence | 0.25 | 2022-08-16 | Adding the user stories/subtasks from the assesment to a jira page | X
Making a plan for this project in confluence and idea page | 0.25 | 2022-08-16 | Made a confluence page to organize my mind and for a better presentation of my thoughts | X
Setting up github | 0.25 | 2022-08-16 | Had a bit of a issue with the .gitignore but I found an default unity gitignore at: https://github.com/github/gitignore/blob/main/Unity.gitignore | X
Researching maze algorithms | 0.66 | 2022-08-16 | Researching different maze algorithms to look which one is the best for this project. I choose performance over quality in the end details about this decision are in the documentation (Research Maze Algorithms)
Researching Kruskal's algorithm for Unity projects | 1 | 2022-08-17 | Found a couple of youtube videos and github pages about Kruskal's algorithm (read document aanpak_kruskals_algorithm for details) but i'm struggling with understanding how it exactly works, I want to figure out how grids/nodes/edges work so that I can implement it myself and not copy paste it from internet. Thinking of making a flowchart so that I can take it step by step
Implemented simple system to create nodes based on height and width | 1 | 2022-08-17 | Made a function to generate nodes based on the height and width given by the user. Struggled a little bit with "calculating" it in the for loop but after a bit of debugging I knew what was wrong and was easily fixable, I put the for loops in the wrong order.
Made function to calculate corners of a grid (Game Object) | 1 | 2022-08-18 | Made a function that can calculate the corners of a game object, I struggled a bit on how to calculate. I wasted a lot of time trying to calculate it with only a transform but after an hour I came to the conclusion to just calculate it with the mesh collider for now. (source: https://answers.unity.com/questions/1833942/how-to-align-gameobjects-based-on-their-corner-not.html)
Trying to correctly place nodes all over the grid | 1 | 2022-08-18 | Trying to correctly place nodes on the grid but currently it works only if the width and height is 10, struggling to find a solution to correctly place nodes for every size. It looks like the problem is with getting the bottom left corner.
Trying to fix placing nodes and a lot of debugging also made a important decision regarding the project. | 1.5 | 2022-08-18 | Tried fixing placing the nodes on the grid by doing a lot of different calculations I do not understand. I made an important decision regarding how I will approach the project, I'm not going to implement Kruskal's algorithm but the "Recursive Backtracker" (source:https://www.youtube.com/watch?v=OutlTTOm17M) Read document: zelfreflectie for more info about the decision to switch to another algorithm.
Implemented recursive backtracker following a tutorial and some refactoring for better readable code | 1.33 | 2022-08-18 | Followed a tutorial on youtube (https://www.youtube.com/watch?v=OutlTTOm17M) to implement the maze algorithm with a visual representation, didn't had any issues with it since its a youtube tutorial. I did some refactoring and more single responsibility, in the future I want to refactor more because some lines doesn't make sense if you do not exactly know what it does.
Made a basic UI for width and height input | 1 | 2022-08-19 | Implemented 2 input fields for width and height, implemented a max/minimal for the input fields, 2 text fields that imply its for width and height and implemented a button to generate maze (button doesnt work yet) thinking of a solution to get the input field and pass them to the maze generator in the most Single Responsibility Way possible. Also set the pivot/anchors for the UI elements
Some UX features for width and height input and made a button that can generate a maze | 0.66 | 2022-08-19 | Implemented a feature that doesn't automatically change the input value of a input field when a user is editing the field (except for when the number goes higher then 250) when a user "deselects" the input field the value and its lower then the minimum number it changes to the minimum number (more detailed description in the function "isEditing", that can be found in the "InputNumberConstraints" script. Also made that a button can generate the maze with the given width/height.
Made a delay input field to slow down the process of building a maze and made the option to regenerate a maze | 1 | 2022-08-19 | Implemented a delay input field that can accept decimals, had to rewrite some logic regarding validating a value but it was not hard. The delay input value is used to delay the process of building a maze and made the option to regenerate a maze. Also made my first build to check the UI elements, it is not perfect yet so I have to look into that.
Implemented a fix for weird scaling/positioning behaviour of UI | 0.15 | 2022-08-20 | Had a "frame" UI element that didn't position/scale well, but I just had to set the anchors to the top left corner after that it looks like the UI is behaving as intended. Watched this youtube video as a reference: https://www.youtube.com/watch?v=QnT-2KxVvyk
Made a function that repositions camera when a maze gets generated (W.I.P) and saw that current algorithm crashes/is too slow for larger mazes | 0.5 | 2022-08-20 | Made a function that repositions the camera based on the maze's width and height, while playing with the width and height values I came to the conclusion the algorithm is way too slow. Since I still have a good amount of hours left before the "20 hour mark" i'm going to search for faster algorithms.
Implemented Eller's algorithm | 2.5 | 2022-08-20 | Succesfully implemented Ellers algorithm, now i'm able to generate a 250x250 maze without Unity crashing. Have to refactor the whole "algorithm" because it is a complete mess, had a lot of struggles with thinking how I can make it more abstract and i'm still thinking how I can do that. Followed a youtube tutorial: (https://www.youtube.com/watch?v=kD-YUSNffFY) Note: there are in total 3 parts.
Refactoring / Debugging and saw that Eller's algorithm implementation doesn’t work properly | 1 | 2022-08-20 | While refactoring and debugging the code of the algorithm I saw the generator doesnt work properly (source: https://gyazo.com/b1b8b2b32aedbef1212aa41485800ec5 ) then I tested it with the source code of the owner and it happened again.
Implemented HuntAndKill Algorithm | 1 | 2022-08-21 | After searching for new algorithms I found the "Hunt and Kill" algorithm (source: https://www.youtube.com/watch?v=IrO4mswO2o4). It works pretty fast, I can generate 250x250 mazes without much performance costs, now I'm going to refactor some code.
Refactored Hunt and Kill algorithm class | 2 | 2022-08-21 | Took the time to understand and refactor the Hunt and Kill algorithm, I am happy with the result. Did not had trouble with anything specific, I was just thinking about how I can make it a bit more abstract and readable. After I had a decent understanding about how the algorithm works, I had no problems with making it more abstract and readable.
Implementing visualization feedback | 1.5 | 2022-08-21 | I'm currently experimenting with adding visual feedback but I'm struggling with how to do it as efficient as possible, I could do it in the update loop but then at high sizes it adds a "delay" on its own and that is not what I want. A while loop on the main thread doesn't work either because the screen won't update until the maze is done generating, an async task doesn't work either because Random.Range() can't be called async. A coroutine seems to work great for now, although I use my "own" formula to calculate a delay instead of WaitForSeconds/WaitForSecondsRealtime i'm a bit concerned that a coroutine gives extra delays which are not intended.
Debugging coroutine delays | 0.66 | 2022-08-21 | After trying to use my own formula to determine a delay (in a coroutine) I saw it was almost a waste to keep it in the project since I want to update the game while generating the maze it is a delay on itself. Instead of making an option to delay a maze generation for X seconds i'm going to make an option to choose if you want to delay the maze generation or not.
Implemented Prim's algorithm on my "own". | 2 | 2022-08-22 | After the "backend" I made yesterday and getting more knowledge about how mazes/grids work I was confident I could implement a maze algorithm without a youtube tutorial, I only used this source: https://weblog.jamisbuck.org/2011/1/10/maze-generation-prim-s-algorithm. At first I was struggling a bit because I had infinity loops, then I had a issue where the maze destroys way more walls then necessary. After debugging I saw that there are "Visited" cells in the frontierCells list (so it will reiterate over a visited cell), as far as I know this is unintended behaviour. For now I used a if statement to check if the frontier cell is visited, but I am still debugging/testing where the issue comes from. | X
Small refactoring of algorithms and documentated the algorithms | 1.15 | 2022-08-22 | Took the time to refactor a little bit of the current algorithms (HuntAndKill/Prims) also documented the code.
Implemented a decent camera positioning when a maze gets generated | 1 | 2022-08-22 | Implemented a feature that repositions the camera when a maze gets generated, I lerp towards the position for a smoother effect. Not entirely happy with the result but I think its decent enough for now.
Remade UI and added option to choose between Prims algorithm and HuntAndKill | 1.15 | 2022-08-22 | Completely remade the UI so that it works on every device also made the option to choose between algorithms, but i'm not entirely happy with how the UIManager interacts with the MazeManager.
Total amount of hours (calculated by myself) | 22.1